# *An Eternity too Late* Breakdown

##  **Budget ($5,300-$5,800)**

**Actors - $1,500**

**Crew - $1,000**

**Traveling - $150**

**Food - $150**

**Equipment - $500**

**Software plugins - $500**

**Campaign rewards - $500-$1,000**

**Marketing - $500**

**Products (DVDs, shirts, etc.) - $500**

**Location - $0**

## **Schedule (5 months)**

**Preproduction: (2 weeks)**

* **Script writing – Complete**
* **Location lineup – 1 week**
* **Auditions – 1 week**

**Production: (4 weeks)**

* **Rehearsals – 1 week**
* **On location shooting – 3 weeks**

**Postproduction: (6 weeks)**

* **Editing – 2 weeks**
* **Special effects and color correction– 4 weeks**

**Release: 3 months**

* **Contact supporters**
* **DVDs**
* **Blu-Ray**
* **Digital release**
* **Initial marketing campaign**